## Sheet1
Related User Story | Task Description | Initial Estimate |  | Amount Remaining After…
|  |  | Assignment | Week 1 | Week 2 | Week 3 | Week 4
That User Story | Code Things…
to be notified by email when notification criteria is met | Agree on a time that the server will check routinely notifications for all users that have an email in their table. At that time, iterate through all the games on each user's watchlist, make api calls for each (abiding by the queue limit of 175) and then for each game/user pair, send an email to that user's email from the server using smtplib and email.message modules. | 10 | Nathan/Luke/Michael | 10 | 7 | 5 | 0
| Encapsulate notification checking in its own python class/module | 4 | Nathan | 3 | 0 | 0 | 0
| Create queue class that all notification checks will be wrapped in to ensure api rules are abided by | 2 | Luke | 2 | 0 | 0 | 0
link my Steam account to SteamScout | Create client-server json exchange for steam import | 8 | Luke | 7 | 3 | 0 | 0
to check my notifications in app | Ask the server for notifications. The server will pull notification status from most recent call to the api for every item on the user's watchlist, compare the prices, and send json that contains the games to construct notifications for. | 5 | Nathan | 3 | 3 | 3 | 0
Other Requirements. | Set up Python server. We'll do it together. Use Dr. Corley's template project | 18 | Luke/Nathan/Michael | 15 | 25 | 18 | 0
| create server requests | 10 | Luke/Nathan/Michael | 8 | 7 | 5 | 0
| connect server requests to client | 10 | Luke/Nathan/Michael | 10 | 10 | 8 | 0
| create test data for the server | 4 | Luke/Nathan/Michael | 1 | 0 | 0 | 0
| create api connections on server | 10 | Luke/Nathan/Michael | 10 | 9 | 5 | 0
[8 empty] | 1 | 69
[8 empty] | 2 | 64
[8 empty] | 3 | 44
[8 empty] | 4 | 0
| Estimate Totals | 81 | 0 | 69 | 64 | 44 | 0