## Sheet1
Need to overestimate here because there is more work we are not thinking of at the moment.
Related User Story | Task Description | Initial Estimate |  | Amount Remaining After…
|  |  | Assignment | Week 1 | Week 2 | Week 3 | Week 4
That User Story | Code Things… | 49 |  | 27 | 50 | 25 | 0
Search Games | Code the browsing page. | 4 | Michael | 1
| Hook the browsing page with functionality to show results from steam api | 4 | Luke/Michael | 3
| Add abstraction layer classes to hide api access | 3 | Luke | 3
Track Games | Create class that manages and maintains a list of games. (Watchlist) | 2 | Luke | 2
| Code ability for user to add games on browsing page to the watchlist class. | 2 |  | 2
Untrack Games | Code the watchlist page. | 2 | Michael | 1
| Link watchlist page with the class that manage's list of games (Watchlist). | 2 | Luke/Michael | 0
| Code ability for user to remove games on watchlist page from their watchlist. | 2 |  | 0
Check Notifications | Code notifications page. | 2 | Michael | 1
| Link notifications page with ability to access steam api and retrieve current/most accurate information. | 4 | Luke/Michael | 3
| Display any notifications that a game on the watchlist is on sale or is below the threshold specified by user. | 4 | Luke/Michael | 2
Edit Tracked Games | Code ability for user to change price threshold for a certain game in the watchlist | 3 |  | 2
N/A (Technical Work needed to support user story work above) | Create encapsulating Game class that holds information about game. | 3 | Luke | 3
| Setup MVVM design pattern for all view classes. | 4 | Luke/Michael | 2
Additional Quality of Life work. | Utilize threads for loading in api data upon startup, as well as when searching for games. | 6 | Luke | 0
| Code user class with user name and password credentials. | 2 | Luke | 2
| Estimate Totals | 49 |  | 27 | 50 | 25 | 0