## Sheet1
Priority | Who | What | Why
1 | user | to put a game on a watchlist | I can view the price of the game
1 | user | to remove games from my watchlist | I can remove games that I am no longer tracking
1 | user | to browse the steam library by entering the name of a game | I can find the games that I want on my watchlist
1 | user | to check my notifications in app | I don't have to exit the app to view notifications if I don't want to | Decided to bump this to second sprint. It makes more sense to tie this in with the server functionality where all of the data is stored, but we have not set up the server yet.
1 | user | specify "cutoff" for item on watchlist | I can get notifications when a game dips below a price point.
2 | user | to be notified by email when notification criteria is met | I can purchase the game at a good price
2 | user | to be able to edit my watchlist | I can reevaluate the price threshold that I am willing to buy the game at.
2 | user | a link to purchase the game in my notifications | I can quickly purchase the game as soon as I get a notification
2 | user | link my Steam account to SteamScout | I can transfer my watch list between devices by signing in
3 | user | have a search history to view games that I have added to my list in the past. | I can easily find games that I have added to my watch list in the past
3 | user | sort my watchlist by sorting factors such as alphabetical order, rating, price, etc. | I can see games that are similar.
3 | user | to search for games by other factors such as genre | I can find a game I want even if I don't remember the name
3 | user | recieve relevant results despite a spelling mistake | I can find a game if I mispress a key
3 | user | the textfields to autopredict what I am typing | I don't have to type so much.
4 | user | to be able to share my watchlist with others | I can share my watchlist with others
4 | user | for games on my watchlist to be automatically removed if I buy the game | I don't continue getting notifications for a game that I already have
4 | user | to import my wishlist from steam into my watchlist | I don't have to manually add games from my wishlist to my watchlist