## Sheet1
Related User Story | Task Description | Initial Estimate |  | Amount Remaining After…
|  |  | Assignment | Week 1 | Week 2 | Week 3 | Week 4
That User Story | Code Things… | Ideal Hours
As a user, I want to put a game on a watchlist. | Create class that manages and maintains a list of game objects. Should be able to add to it. | 2 | Luke | 0 | 0 | 0 | 0
| Create a Game object that encapsulates details about game. | 2 | Luke | 0 | 0 | 0 | 0
| Create watchlist page fxml and code behind | 3 | Michael | 1 | 1 | 0 | 0
| Create browsing page fxml and code behind | 3 | Michael | 1 | 1 | 0 | 0
| Simulate login by creating a mock user. | 2 | Luke | 0 | 0 | 0 | 0
| Create method in the view model that the browsing page can call to add the game to the watchlist | 2 | Luke | 2 | 2 | 0 | 0
As a user, I want to remove games from my watchlist. | Create method in the view model that the watchlist page can call to remove the game from the watchlist | 2 | Luke | 2 | 2 | 2 | 0
As a user, I want to search games. | Create class that maintains list of steam games. | 2 | Luke | 2 | 2 | 2 | 0
| Create method in the view model that finds games whose title contains a given search keyword | 2 | Luke | 2 | 2 | 2 | 0
As a user, I want to change notification criteria for games on my watchlist. | Create change notification criteria page fxml and code behind | 3 | Luke | 2 | 2 | 0 | 0
| Create a notification criteria object that encapsulates the information | 2 | Luke | 2 | 2 | 0 | 0
| Store the notification criteria for each game in the watchlist. | 2 | Luke | 2 | 2 | 0 | 0
As a user, I want to manually check notifications. | Create the notification page fxml and code behind | 3 | Michael | 1 | 1 | 0 | 0
| Create a notification object that encapsulates the information. | 2 | Nathan | 1 | 0 | 0 | 0
| Create a collection wrapper class that maintains notifications. | 2 | Nathan | 2 | 2 | 1 | 0 | 0 | 41
[8 empty] | 1 | 28
[8 empty] | 2 | 24
[8 empty] | 3 | 10
Other Requirements. | Create Singleton ViewModel stub. | 2 | Luke/Michael/Nathan | 1 | 1 | 0 | 0 | 4 | 0
| Connect UI to model classes to display information. | 5 | Luke/Michael/Nathan | 4 | 3 | 1 | 0
| Create Navigation Bar |  | Michael | 3 | 1 | 2 | 0
| Estimate Totals | 41 | 0 | 28 | 24 | 10 | 0