## Sheet1
Related User Story | Task Description | Initial Estimate |  | Amount Remaining After…
|  |  | Assignment | Week 1 | Week 2 | Week 3 | Week 4
That User Story | Code Things…
to be notified by email notifications when notification criteria is met
| Create email handler class in python for email notifications | 3 | Michael | 3 | 0 | 0 | 0
| Move the watchlistupdater to on its own thread that runs with the server instead of a standalone module. | 10 | Nathan | 10 | 10 | 0 | 0
| Wrap all access to file i/o to a dedicated class that has synchronization blocks around a static lock when accessing the files. | 12 | Nathan/Luke | 12 | 12 | 0 | 0
| Display why the notification is being sent i.e. show the game info and link to steam page | 3 | Michael | 1 | 0 | 0 | 0
to be able to share my watchlist with others | Create ShareWatchlistPage fxml and code behind (featuring a multiselection list view) | 9 | Luke | 9 | 9 | 0 | 0
Can get to the share watchlist page through a button on the watchlist page.
Enter a username into a text field and pull the watchlist for that user. That user's watchlist is populated into the listview. Then
all games not already on the logged in user's watchlist are displayed in the listview. The user can then select the games they want
and push an add to watchlist button.
to have the textfields autopredict what I am typing | Incorporate trie data structure with tests | 5 | Luke | 5 | 0 | 0 | 0
| Create the autopredict fxml for the context menu and display it appropriately. Basically hook it up to code behind. | 2 | Luke | 2 | 0 | 0 | 0
Limit autopredict to show maybe after the 2nd or 3rd keystroke.
| Make Auto-predict results have the correct letter-casing. | 3 | Nathan | 3 | 0 | 0 | 0
link my Steam account to SteamScout | FInish writing the steamwishlist link service on the server and test it. | 11 | Luke/Nathan | 0 | 0 | 0 | 0
| Create button on watchlist page that links to a link steam account pop up. The pop up will ask for the user's steam account id as well as whether or not the server should store the account id. | 3 | Luke | 0 | 0 | 0 | 0
| Then when they hit a link button on the pop up, it will contact the server. The server will make the api call and get back the steam wishlist. Then, all games on the wishlist are added to the user's watchlist. | 7 | Luke | 0 | 0 | 0 | 0
a link to purchase the game in my notifications | Create NotificationListCell implementation that displays all relevant information. Then set the cell factory on the notifications page. | 3 | Michael | 3 | 3 | 0 | 0
| The steam link should be an anchor that pulls up the web browser to that link. | 2 | Michael | 2 | 2 | 0 | 0
Additional Requirements | Populate browse page with games without having to search | 2 | Michael | 2 | 2 | 0 | 0
| Remove the steamid from the set notification criteria popup | 2 | Michael | 2 | 2 | 0 | 0
| Estimate Totals | 77 |  | 54 | 40 | 0 | 0
[7 empty] | 4 | 77
[7 empty] | 3 | 54
[7 empty] | 2 | 40
[7 empty] | 1 | 0